# SOFTWARE DEVELOPMENT AGREEMENT

This Software Development Agreement (“Agreement”) is made and executed on this ___ day of __________ 20___, by and between [Service Provider Legal Name], having its principal place of business at [Address], hereinafter referred to as the “Service Provider”, and [Client Legal Name], having its registered office at [Address], hereinafter referred to as the “Client”.

Both parties hereby agree to the terms and conditions set forth in this Agreement.

## 1. PURPOSE OF THE AGREEMENT

The purpose of this Agreement is to define the scope, deliverables, timelines, commercial terms, responsibilities, and legal obligations under which the Service Provider shall design, develop, test, deploy, and support a customized web-based software system for the Client.

## 2. PROJECT OVERVIEW

The Service Provider shall develop a secure, role-based, and scalable software solution that enables centralized administration, volunteer operations, hostel management, financial transactions, digital office register maintenance, and reporting functionality, in accordance with the specifications outlined herein.

## 3. SCOPE OF WORK

### 3.1 Modules Covered

| Module No. | Module Name | Scope Description |
| --- | --- | --- |
| 1 | Authentication & User Access | Secure login system with role-based permissions for Admin, Sub-Admin, Volunteer & Hostel users |
| 2 | Admin Panel | Management of users, students, memberships, tournaments, certificates & reports |
| 3 | Volunteer Panel | Student onboarding, payment collection & tournament participation |
| 4 | Hostel Management Panel | Admissions, room allocation, fee tracking & occupancy monitoring |
| 5 | Payment & Finance | Online and offline payments, approvals & financial reports |
| 6 | Register Maintenance | Digitization of 16 statutory and operational office registers |
| 7 | UI/UX Design | Fully responsive dashboards for all user roles |
| 8 | Testing & Deployment | System validation, deployment & user training |
| 9 | Subscription Services | Database setup, hosting coordination & auxiliary services |

## 4. FUNCTIONAL SPECIFICATIONS

### 4.1 Admin Panel Capabilities

- Creation, modification, activation and deactivation of user roles

- Membership plan configuration including pricing, duration & benefits

- Tournament creation, participant allocation and tracking

- Centralized student profile management including academic and sports records

- Review, approval and reconciliation of payments

- Automated generation and tracking of digital certificates

### 4.2 Volunteer Panel Capabilities

- Student registration with mandatory photo upload

- Membership assignment and fee collection

- Tournament registration and event participation

- Match result submission including winners and losers

- Performance monitoring and activity dashboards

### 4.3 Hostel Management Capabilities

- Hostel admission processing and profile management

- Allocation of blocks, rooms and beds

- Hostel fee configuration and payment status monitoring

- Student check-in and check-out management

- Occupancy, vacancy and utilization reports

- Attendance, discipline and remark records

### 4.4 Register Maintenance Module

The system shall include digitization and maintenance of the following 16 Office Registers:

- Visitors Register

- Property Register

- Employee Attendance Register

- Inward & Outward Register

- Office Maintenance Register

- Membership Register

- Certificate Issue Register

- Ledger Book

- Cash Book

- Cheque Issue Register

- Donor Register

- Volunteer Register

- Phone Call Log Book

- Complaint & Feedback Register

- To & Fro Register

- Office Meetings & Appointment Register

Each register shall provide:

- Create, update and view operations

- Advanced search and date-based filtering

- Structured digital records for auditing and reporting

## 5. PROJECT EXECUTION TIMELINE

| Phase | Description | Duration |
| --- | --- | --- |
| Phase 1 | Requirement confirmation, UI/UX & database design | 2 Weeks |
| Phase 2 | Core module development - Part 1 | 3 Weeks |
| Phase 3 | Core module development - Part 2 | 3 Weeks |
| Phase 4 | Payment, registers & certificates implementation | 4 Weeks |
| Phase 5 | Testing, training & production deployment | 2 Weeks |

Total Estimated Project Duration: 14 Weeks
 (Timeline shall commence from the date of advance payment receipt.)

## 6. MILESTONES & DELIVERABLES

| Milestone | Deliverables | Target Completion |
| --- | --- | --- |
| Milestone 1 | Approved requirements, UI/UX & database schema | End of Week 2 |
| Milestone 2 | Admin, Volunteer modules | End of Week 8 |
| Milestone 3 | Hostel modules, Integration Testing | End of Week 10 |
| Milestone 4 | Payment gateway, digital registers & certificates | End of Week 12 |
| Milestone 5 | Final testing, deployment & knowledge transfer | End of Week 14 |

## 7. COMMERCIAL TERMS & PAYMENT STRUCTURE

### 7.1 Total Contract Value

Total Contract Value:
 ₹3,00,000 (Rupees Three Lakh Only)

The contract value includes development, testing, deployment, documentation, training, and post-deployment support as defined herein.

Applicable statutory taxes, including GST, shall be charged extra as per prevailing laws.

### 7.2 Advance Payment & Project Initiation

- Advance Amount: ₹50,000 (Non-refundable)

- The advance payment is mandatory for project initiation

- No development activity shall commence until the advance payment is received and acknowledged

- Project timelines shall be calculated from the date of advance payment confirmation

### 7.3 Milestone-Based Payment Schedule (Balance ₹2,50,000)

| Milestone | Description | Amount (₹) |
| --- | --- | --- |
| Milestone 1 | UI/UX & database finalization | ₹50,000 |
| Milestone 2 | Core module development - Part 1 | ₹50,000 |
| Milestone 3 | Core module development - Part 2 | ₹50,000 |
| Milestone 4 | Payment, registers & certificates | ₹50,000 |
| Milestone 5 | Testing, deployment & handover | ₹50,000 |
| Total Balance |  | ₹2,50,000 |

### 7.4 Payment Conditions

- Payments shall be released upon successful milestone delivery and approval

- Invoices must be cleared within 7 working days

- Non-payment or delayed payment may result in suspension of work

- Final deliverables, source code and credentials shall be released only upon receipt of full payment

## 8. CLIENT OBLIGATIONS

- Provide timely inputs, approvals and feedback

- Share all required branding, content and operational data

- Ensure adherence to payment schedules

- Designate an authorized representative for coordination

- Provide subscriptions to online database (mongodb), hosting, domain and other services. These will be owned by the Client.

## 9. SERVICE PROVIDER OBLIGATIONS

- Deliver the system in accordance with the agreed scope

- Maintain confidentiality and data security

- Rectify defects during the support period

- Provide system training and technical documentation

## 10. INTELLECTUAL PROPERTY & OWNERSHIP

- All source code shall be transferred to the Client upon full payment

- Database ownership, schema and credentials shall be handed over

- Client shall have full rights to host, modify or extend the system

## 11. CHANGE MANAGEMENT

- Any requirement beyond this scope shall constitute a Change Request

- Change Requests shall be evaluated, quoted and approved in writing

- Timelines and costs may be revised accordingly

## 12. SUPPORT & MAINTENANCE

- Free support for 12 months from deployment date

- Includes bug fixes and minor functional adjustments

- AMC services available post free-support period

## 13. CONFIDENTIALITY

Both parties shall maintain confidentiality of all proprietary, technical and business information exchanged during the course of this engagement.

## 14. ACCEPTANCE & EXECUTION

By signing below, both parties confirm that they have read, understood and agreed to all terms and conditions of this Agreement.

### CLIENT AUTHORIZATION

Name: ______________________________
 Designation: ________________________
 Organization: _______________________
 Signature: _________________________
 Date: ______________________________

### SERVICE PROVIDER AUTHORIZATION

Name: ______________________________
 Designation: ________________________
 Organization: _______________________
 Signature: _________________________
 Date: ______________________________